## Slide 1: 120GHz Imaging Radar
Team 40:
Huyen Vy Pham: Team lead
Aaron McCarville: Lead hardware design
Noah Gaffney: Hardware design and testing
Gunnar Hageman: Embedded programming
Benjamin Podjenski: Software programming
Client:
Professor Mohammad Tayeb Al Qaseer
Advisor:
Professor Mohammad Tayeb Al Qaseer

## Slide 2: Project Vision
Project goal: It is to build a 120 GHz millimeter wave (mm-wave) imaging radar. The system will be based on TRA_120_045 radar chip. There are two subsystems in the radar:
  RF circuit (radar IC and phased-locked-loop (PLL) circuitry).
  ADC circuit with FPGA
  A GUI
Usage:
  It is mainly used for the Non-destructive Evaluation do object imaging and flaw detection inside of model.
Approach:
  Building and testing two subsystems (RF and ADC boards) separately.
  Programming the Alchitry Au to control peripheral IC's through SPI.
  Configuring the Alchitry Au to send ADC data to Host PC via USB.
  Building a PC application for user to communicate to the system.
  Testing the system as a whole for functionality.
  Using the system to conduct radar imaging experiments in the microwave lab at CNDE.

## Slide 3: Conceptual/Visual Sketch
RF Board: Radar IC and PLL circuitry
ADC Board: Low Pass Filter, Amplifier, and ADC
FPGA Board: SPI, UART, and FTDI/ USB communication
User Interface: Data transfer and display; control signal
Control signal
Control Signal
Control signal
Data
Data
Data

## Slide 4: System Design
TRA 045 chip
Internal diagram
Antenna on chip

## Slide 5: System Design
Detailed design (components/modules design) for RF Board – The Phase Lock Loop circuitry
Phase Lock Loop circuitry
VCO
Low Pass filter
N Divider
X
Reference frequency
RF frequency

## Slide 6: System Design
Detailed design (components/modules design) for ADC Board
IFIp
IFIn
IFQp
IFQn
ADC
ADC
IFI
IFQ
Notes: Should talk about the cutoff frequency of the LPF and then the spec for ADC

## Slide 7: System Design
Detailed design (components/modules design) for Signal Path
RF Board
ADC Board
Alchitry Au
Host PC
SPI
IFI and IFQ data
Control signal
Control signal
FTDI Chip
JTAG
UART
ARTIX 7
IFI and IFQ data / Control
USB 2.0
GUI
Notes: Should talk about the cutoff frequency of the LPF and then the spec for ADC

## Slide 8: System Design
User Interface Prototype
FPGA
Control signal
Raw Data (IFI and IFQ)

## Slide 9: System Design
GUI software:
Front-end: Django Framework.
Webpage Hosting: Raspberry Pi using an Apache webserver.
Embedded Programming: Xilinx platform, Vivado (Hardware) and Vitis (Software).
Communication between PC and FPGA: FTDI.
RF and ADC board: KiCad.
Lens Modeling: CST software.
Testing: Spectrum Analyzer.
HW/SW platforms, technology, frameworks, standards

## Slide 10: Project Plan
Task Decomposition:
RF board (based on Evaluation bard)
ADC Board
FPGA Research and Learning
GUI Programming
Lens Modeling
ADC Board PCB and Schematic
FPGA Programming
Connecting the Data Sequencing with RF subsystem and FPGA and GUI Programming

## Slide 11: Project Plan – Schedule/Milestones
Milestone | Task | Completion | Expected Completion Date
Radar Board Design |  |  | 10/23/2023
 | Schematic Design | 100% | 9/23/2023
 | Layout Design | 100% | 10/23/2023
Radar Board Testing |  | 100% | 1/26/2024
 | PLL on the board to be locked at a single frequency, and it is detected by Spectrum Analyzer | 100% | 11/10/2023
 | PLL on the board can sweep a range of frequency and can be detected by Spectrum Analyzer | 100% | 11/30/2023
 | Conducting imaging using the Radar Board with NIDAQ | 100% | 1/26/2024

## Slide 12: Project Plan – Schedule/Milestones
Milestone | Task | Completion | Expected Completion Date
ADC Board Design |  | 100% | 2/9/2024
 | Schematic Design | 100% | 12/6/2023
 | Layout Design | 100% | 2/9/2024
ADC Board Testing |  |  | 3/9/2024
 | Testing the functionality: A signal generator will send a voltage sine wave is sent to the ADC board. The raw ADC data is collected by the FPGA and is plotted by the host to be compared to the original voltage sine wave | 30% | 
Integrating the ADC board and RF board |  | 0% | 3/23/2024

## Slide 13: Project Plan – Schedule/Milestones
Milestone | Task | Completion | Expected Completion Date
FPGA programing |  |  | 3/31/2024
 | Sending and echoing commands through UART | 100% | 2/10/2024
 | Communicating with the GUI through UART | 100% | 2/17/2024
 | Sending and echoing commands through SPI | 30% | 3/10/2024
 | Sending commands to program PLL through SPI |  | 3/23/2023
 | Sending commands to program ADC through SPI |  | 3/31/2024
 | Sending commands to program the Amplifier |  | 3/31/2024

## Slide 14: Project Plan – Schedule/Milestones
Milestone | Task | Completion | Expected Completion Date
GUI programing |  |  | 3/31/2024
 | Communicating with the FPGA through UART | 100% | 2/10/2024
 | Sending control data to PLL to FPGA |  | 3/23/2024
 | Receiving data from the DAC through FPGA |  | 3/31/2024
 | Live updating the data on the GUI |  | 3/23/2024
 | Using Raspberry Pi to host the GUI |  | 3/23/2024
Design a cage for the product |  | 50% | 3/31/2024
Lens design and print for the radar |  | 100% | 11/31/2023

## Slide 15: Current Design

## Slide 16: Challenges and Solutions
Getting data transferred from the GUI to the Amplifier through SPI
Reading from the ADC using the FPGA

## Slide 17: Summary
Overall progress: Following the timeline and making progress every week.
Plan for the remaining of the project: Focus more on FPGA programing and GUI.
Targeting completion date: March 31st